## IPI DRB Minutes
|  | IBIDEN PHILIPPINES, INC. | [18 empty] | DRB/MRB No. : |  | D-FVI-19-10-002
|  | DRB/MRB REPORT MINUTES | [18 empty] | RFC No. : |  | 30-1019-0024
Theme: |  |  | Sr dent due to manual transfer at FVI
Meeting Date : |  |  | 28-Oct-19 | [12 empty] | Originated by : |  |  |  | Maribel Awa
Meeting Time: |  |  | 1000H-1020H | [17 empty] | Name /Block
Meeting Place: |  |  | FVI DMM Meeting Area | [12 empty] | Approved by :
Chairman: |  |  | Maribel Awa | [16 empty] | Originator ASM/SM/DGM/GM
Block: |  |  | FVI
Attendees : |  |  | Manufacturing |  |  | Engineering/NPD |  |  |  | Facilities/EE |  |  |  |  | QA/QC |  |  |  |  | PPIC/CSE |  |  |  | Other
|  |  | Bhel |  |  |  | Janice |  |  |  | Dec |  |  |  |  | Jake |  |  |  |  | Janette
[7 empty] | Jopay | [13 empty] | Ann
<1>PROBLEM STATEMENT : (Put another sheet if multiple lots was discovered affected)
DEFECT ISSUE: |  |  | Sr dent due to manual transfer at FVI |  | # | PRODUCT/MODEL AFFECTED |  |  |  | PRODUCT FAMILY |  |  | LEDGER NO. |  | PRODUCT SIZE |  | LOT NUMBER |  |  | AFFECTEDLAYER |  | AFFECTED PANEL |  | AFFECTED UNIT OR IF PERCENTAGE
DATE/TIME OCCURRED: |  |  | Oct-28-19 |  | 1 | RENOIR |  |  |  | UTC |  |  | 022-1708 |  | 25x35 |  | P7882590 |  |  | n/a |  | n/a |  | 459 units/10.19%
PROCESS DETECTED: |  |  | AVI |  | 2
PROCESS AFFECTED: |  |  | AVI |  | 3
# OF AFFECTED LOTS : |  |  | 1 |  | 4
WHO DETECTED: |  |  | PV inspectress |  | 5
6
WHAT IS THE PROBLEM DIFFERENCE FROM NORMAL TO ABNORMAL SITUATION? CHANGING POINT? DISCUSS THE FLOW. (Indicate 5W and 1H)
THE AGENDA ITEM IS RECURRENCE? |  |  |  | RECURRENCE |  |  |  | NEW |  |  |  | Recurrence Definition |  |  |  | 1. Rootcause is clear happened in same MC and parts 2. Rootcause is not clear but same issue 3. The Action was not proliferated to other process and machine but it was discussed during the meeting
THE AGENDA ITEM IS ESCAPEE? |  |  |  | YES |  |  |  | NO
PROBLEM CATEGORY |  |  | MAN |  | MACHINE |  |  |  | METHOD |  |  | MATERIAL |  |  | MEASUREMENT |  |  |  | ENVIRONMENT |  |  |  | OTHERS
DRB CLOSING RANK |  |  | RANK 1 |  | RANK 2 |  |  |  | RANK 3 |  |  | RANK 4 |  |  | RANK 5 |  |  |  | OTHERS
<2> INVESTIGATION/IDENTIFICATION OF AFFECTED AREA, SITUATION (Define the phenomenon, mode and tendency occurrence,Etc.)
1. Metal part of Handy vacuum pen touched the units resulted to dent.
<3> CONTAINMENT ACTION (Note: Do not disable the interlock system when doing the action) | [16 empty] | Responsible |  |  | Completion Date |  |  | Status
Name / Block
1. Remove affected portable handy vacuum pen & use vacuum pen for transferring | [16 empty] | Bhel/Mfg |  |  | 2019-10-30 |  |  | Done
<4> DISPOSITION OF AFFECTED LOT AND RISK ASSESSMENT
Assessment Item (# of sample/Method) |  |  |  | Responsible Name / Block |  |  |  | Completion Date |  |  | Assessment Result (No Good/TTL QTY) | [5 empty] | Judgment (OK/NG) |  |  | Final Disposition
1. 100% inspection |  |  |  | MFG Bhel/QC Jake |  |  |  | 2019-10-29 |  |  | No Good/ 459 units | [5 empty] | NG
[21 empty] | Proceed |  | Qty : ______________________________
[21 empty] | Piece Out |  | Qty : _459 units_ Pnl #: _____________
[21 empty] | Sheet Out |  | Qty : ______________________________
[21 empty] | Lot Out |  | Qty : ______________________________
SDR
Risk Assessment Category | [11 empty] | Remarks
|  | Low |  | Medium |  |  |  |  | High |  |  | ________________________
<5>ACTION REQUIRED (Note: Do not disable the interlock system when doing the action)
Action Request | [10 empty] | Responsible Name / Block | [5 empty] | Completion Date |  |  | Detail Results
1. Follow up the lead time of request spare of stage block | [10 empty] | MFG Bhel | [5 empty] | 2019-11-04 |  |  | 20-Nov estimated of arrival
2. Consider the 2nd tooling at AVI for BCOM products | [10 empty] | MFG Beth | [5 empty] | 2019-11-04 |  |  | Done
3. Consider the transferring of units in AVI loading | [10 empty] | PPIC Janette | [5 empty] | 2019-11-04 |  |  | Done
<6> ROOTCAUSE GENERATION/ANALYSIS <WHY ANALYSIS by 5M1E, DESIGN AND CAPABILITY>
1. FACTOR GAP ANALYSIS
| Problem/Issue |  | Gap Type |  | 1st why |  |  |  |  | 2nd why | [5 empty] | 3rd why | [5 empty] | 4th why |  |  | 5th why
| Sr dent on PB |  | Technical
|  |  | Systemic |  | Metal has contact on units surface |  |  |  |  | Due to improper usage of portable handy vacuum pen | [5 empty] | Optr assigned not properly trained
Detection
2. FINAL ROOT CAUSE and MECHANISM OF AFFECTED ISSUE
<7> CORRECTIVE ACTION | [13 empty] | Responsible |  |  |  | Completion Date |  |  | Status |  |  | Need CN & DR?
[14 empty] | Name / Block | [9 empty] | Yes | No
1. Re dissemination of members | [14 empty] | Bhel/Mfg |  |  | 2019-11-08 |  |  |  | Open
<8> PREVENTIVE ACTION | [13 empty] | Responsible |  |  |  | Completion Date |  |  | Status |  |  | Need CN & DR?
[14 empty] | Name / Block | [9 empty] | Yes | No
<9> PROLIFERATION | [16 empty] | Responsible |  |  | Completion |  |  | Status
[17 empty] | Name / Sign |  |  | Date
Product |  | Block | Process/line |  | Machine |  |  | Proliferate Item
1
2
<10>AMOUNT OF LOSS . The total sum_________________
Product |  |  |  |  | Unit Qty | [8 empty] | Amount of Loss | [6 empty] | Remarks
<11> CLOSING APPROVAL (The approver person in charge should put details of the validation and closing confirmation result)
The Validation activity | [17 empty] | Closing Approver |  |  |  |  | Closing Date
ASM Gloria Reyes
QA-SCAR-MRB-02-00-01 Rev. 11

## Sheet1
10.19%