## IPI DRB Minutes
|  | IBIDEN PHILIPPINES, INC. | [17 empty] | DRB/MRB No. : |  | D-VF-19-12-001
|  | DRB/MRB REPORT MINUTES | [17 empty] | RFC No. : |  | 50-1119-0241
Theme: |  |  | Small Via
Meeting Date : |  |  | 04-Dec-19 | [11 empty] | Originated by : |  |  |  | Rowena Flores
Meeting Time: |  |  | 1400h- 1500h | [16 empty] | Name /Block
Meeting Place: |  |  | MP Office | [11 empty] | Approved by : |  |  |  | Loida Ribeiro
Chairman: |  |  | R. Flores | [15 empty] | Originator ASM/SM/DGM/GM
Block: |  |  | VF
Attendees : |  |  | Manufacturing |  |  | Engineering/NPD |  |  | Facilities/EE |  |  |  |  | QA/QC |  |  |  |  | PPIC/CSE |  |  |  | Other
|  |  | Whena |  |  | Owa |  |  | Toto |  |  |  |  | Leo
|  |  | Mavic |  |  | Gladys |  |  | Stephen
|  |  | Horai |  |  | Shelle |  |  | Neil
|  |  | Loida |  |  | Glenda
<1>PROBLEM STATEMENT : (Put another sheet if multiple lots was discovered affected)
DEFECT ISSUE: |  |  | Small Via |  | # | PRODUCT/MODEL AFFECTED |  |  | PRODUCT FAMILY |  |  | LEDGER NO. |  | PRODUCT SIZE |  | LOT NUMBER |  |  | AFFECTEDLAYER |  | AFFECTED PANEL |  | AFFECTED UNIT OR IF PERCENTAGE
DATE/TIME OCCURRED: |  |  | Nov-28-19 |  | 1 | Cavecreek S&R |  |  | CS |  |  | 770-4356 |  | 27X27 |  | P7932850 |  |  | 2-3F |  | 17-32 |  | 50%
PROCESS DETECTED: |  |  | Laser |  | 2 | Tunnel Creek |  |  | CS |  |  | 770-2582 |  | 22x22 |  | P7932750 |  |  | 2-3F |  | 17-32 |  | 50%
PROCESS AFFECTED: |  |  | Laser |  | 3
# OF AFFECTED LOTS : |  |  | 1 |  | 4
WHO DETECTED: |  |  |  |  | 5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
WHAT IS THE PROBLEM DIFFERENCE FROM NORMAL TO ABNORMAL SITUATION? CHANGING POINT? DISCUSS THE FLOW. (Indicate 5W and 1H)
THE AGENDA ITEM IS RECURRENCE? |  |  |  | RECURRENCE |  |  | NEW |  |  |  | Recurrence Definition |  |  |  | 1. Rootcause is clear happened in same MC and parts 2. Rootcause is not clear but same issue 3. The Action was not proliferated to other process and machine but it was discussed during the meeting
THE AGENDA ITEM IS ESCAPEE? |  |  |  | YES |  |  | NO
PROBLEM CATEGORY |  |  | MAN |  | MACHINE |  |  | METHOD |  |  | MATERIAL |  |  | MEASUREMENT |  |  |  | ENVIRONMENT |  |  |  | OTHERS
DRB CLOSING RANK |  |  | RANK 1 |  | RANK 2 |  |  | RANK 3 |  |  | RANK 4 |  |  | RANK 5 |  |  |  | OTHERS
<2> INVESTIGATION/IDENTIFICATION OF AFFECTED AREA, SITUATION (Define the phenomenon, mode and tendency occurrence,Etc.)
<3> CONTAINMENT ACTION (Note: Do not disable the interlock system when doing the action) | [15 empty] | Responsible |  |  | Completion Date |  |  | Status
Name / Block
1. LSH78 Stop loading for all GX13 products | [15 empty] | MFG/Engg |  |  | TBD
2. Power adjustment for LSH67 | [15 empty] | Engg m'Glenda |  |  | 2019-11-28 |  |  | Done
<4> DISPOSITION OF AFFECTED LOT AND RISK ASSESSMENT
Assessment Item (# of sample/Method) |  |  |  | Responsible Name / Block |  |  | Completion Date |  |  | Assessment Result (No Good/TTL QTY) | [5 empty] | Judgment (OK/NG) |  |  | Final Disposition
1. P7932850 1st occurrence: LSH78 Sheet out Small via after PNP IPP measurement |  |  |  | MFG |  |  | ww49.3 | [8 empty] | NG
1. P7932750 2nd occurrence: LSH67 Sheet out Small via after PNP IPP measurement |  |  |  | MFG |  |  | ww49.4 | [8 empty] | NG |  |  |  | Proceed |  | Qty : ______________________________
[20 empty] | Piece Out |  | Qty : _______ Pnl #: ________________
[20 empty] | Sheet Out |  | Qty : ______________________________ | 17-32 Panels (LSH78), 17-32 Panel (LSH67)
[20 empty] | Lot Out |  | Qty : ______________________________
SDR
Risk Assessment Category | [10 empty] | Remarks
|  | Low |  | Medium |  |  |  | High |  |  | ________________________
<5>ACTION REQUIRED (Note: Do not disable the interlock system when doing the action)
Action Request | [9 empty] | Responsible Name / Block | [5 empty] | Completion Date |  |  | Detail Results
1. Request allocation for LSH78 for Engg Power DOE (maximum of 4hrs) | [9 empty] | Engg s'Owa | [5 empty] | TBD
2. Gather Tool maker data vs gap | [9 empty] | MFG Whena | [5 empty] | ww50.1
3. Allocation for GX13 Optimization for 2P4B- aligned on PM MC. (maximum of 2hrs) | [9 empty] | MFG Whena | [5 empty] | ww49.2 |  |  | ww49.2- LSH90
4. Disseminate for Temporary action that need VIA measurement for GX13 on 1st loading on 2P4B mc. | [9 empty] | MFG Whena | [5 empty] | ww50.1
5. Power logs for LSH67 and LSH78 | [9 empty] | Engg s'Owa | [5 empty] | ww49.3
6. T9 Checking prior GX13 loading on 2P4B (Non load for GX13 for atleast 1week) | [9 empty] | Engg sustaining | [5 empty] | start implementation
7. Allocate additional LSH MC Capable for loading of 120um. | [9 empty] | Engg S'Owa | [5 empty] | ww49.5
<6> ROOTCAUSE GENERATION/ANALYSIS <WHY ANALYSIS by 5M1E, DESIGN AND CAPABILITY>
1. FACTOR GAP ANALYSIS
| Problem/Issue |  | Gap Type |  | 1st why |  |  |  | 2nd why | [5 empty] | 3rd why | [5 empty] | 4th why |  |  | 5th why
Technical
Systemic
Detection
2. FINAL ROOT CAUSE and MECHANISM OF AFFECTED ISSUE
<7> CORRECTIVE ACTION | [12 empty] | Responsible |  |  |  | Completion Date |  |  | Status |  |  | Need CN & DR?
[13 empty] | Name / Block | [9 empty] | Yes | No
<8> PREVENTIVE ACTION | [12 empty] | Responsible |  |  |  | Completion Date |  |  | Status |  |  | Need CN & DR?
[13 empty] | Name / Block | [9 empty] | Yes | No
<9> PROLIFERATION | [15 empty] | Responsible |  |  | Completion |  |  | Status
[16 empty] | Name / Sign |  |  | Date
Product |  | Block | Process/line |  | Machine |  | Proliferate Item
1
2
<10>AMOUNT OF LOSS . The total sum_________________
Product |  |  |  |  | Unit Qty | [7 empty] | Amount of Loss | [6 empty] | Remarks
<11> CLOSING APPROVAL (The approver person in charge should put details of the validation and closing confirmation result)
The Validation activity | [16 empty] | Closing Approver |  |  |  |  | Closing Date
ASM Gloria Reyes
QA-SCAR-MRB-02-00-01 Rev. 11