## IPI DRB Minutes
|  | IBIDEN PHILIPPINES, INC. | [17 empty] | DRB/MRB No. : |  | D-BE-19-03-001
|  | DRB/MRB REPORT MINUTES | [17 empty] | RFC No. : |  | 24-0319-0244
Theme: |  |  | DRB Rank5 BE Dent on BGA at OS Test #24
Meeting Date : |  |  | Mar 14 - Mar 19 | [11 empty] | Originated by : |  |  |  | M. Ramores-Awa
Meeting Time: |  |  | Start: 1030H |  | End: 1130H | [14 empty] | Name /Block
Meeting Place: |  |  | FVI Meeting Area | [11 empty] | Approved by : |  |  |  | E. Fruelda/ R. Vergara
Chairman: |  |  | M. Capuno | [15 empty] | Originator ASM/SM/DGM/GM
Block: |  |  | FVI1
Attendees : |  |  | Manufacturing |  |  | Engineering/NPD |  |  | Facilities/EE |  |  |  |  | QA/QC |  |  |  |  | PPIC/CSE |  |  |  | Other
|  |  | Bhel/Beth |  |  | Jigs |  |  |  | Rai |  |  |  |  | Rhona/Lanie/Jake |  |  |  |  | Tromz |  |  | MTT: Peng/Erhen
|  |  | Mitch/Bryan/Maruno/Shin | [19 empty] | JA: She
<1>PROBLEM STATEMENT : (Put another sheet if multiple lots was discovered affected)
DEFECT ISSUE: |  |  | Dent on Bga |  | # | PRODUCT/MODEL AFFECTED |  |  | PRODUCT FAMILY |  |  | LEDGER NO. |  | PRODUCT SIZE |  | LOT NUMBER |  |  | AFFECTED LAYER |  | AFFECTED PANEL |  | AFFECTED UNIT OR IF PERCENTAGE
DATE/TIME OCCURRED: |  |  | 2019-03-13 |  | 1 | KBL 4+2 LGA |  |  | FCLGA 14 |  |  | 775-7000 |  | 37.5x37.5 |  | P7736300 |  |  | n/a |  | n/a |  | 820 units (23.5%)
PROCESS DETECTED: |  |  | AVI (PV) |  | 2 | KBL 4+2 LGA |  |  | FCLGA 14 |  |  | 775-7000 |  | 37.5x37.5 |  | P7736610 |  |  | n/a |  | n/a |  | 1731 units (49.7%)
PROCESS AFFECTED: |  |  | AVI |  | 3 | KBL 4+2 LGA |  |  | FCLGA 14 |  |  | 775-7000 |  | 37.5x37.5 |  | P7645840 |  |  | n/a |  | n/a |  | 1488 units (52.7%)
# OF AFFECTED LOTS : |  |  | 4 lots |  | 4 | KBL 4+2 LGA |  |  | FCLGA 14 |  |  | 775-7000 |  | 37.5x37.5 |  | P7728090 |  |  | n/a |  | n/a |  | 167 units (5.09%),9/63 units inline detection
WHO DETECTED: |  |  | FVI |  | 5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
WHAT IS THE PROBLEM DIFFERENCE FROM NORMAL TO ABNORMAL SITUATION? CHANGING POINT? DISCUSS THE FLOW. (Indicate 5W and 1H)
WHAT : Dent on BGA
WHEN: March 13, 2019
WHERE: FVI inspection
WHY: n/a
WHO: FVI inspector
HOW: Inspection
THE AGENDA ITEM IS RECURRENCE? |  |  |  | RECURRENCE |  |  | NEW |  |  |  | Recurrence Definition |  |  |  | 1. Rootcause is clear happened in same MC and parts 2. Rootcause is not clear but same issue 3. The Action was not proliferated to other process and machine but it was discussed during the meeting
THE AGENDA ITEM IS ESCAPEE? |  |  |  | YES |  |  | NO
PROBLEM CATEGORY |  |  | MAN |  | MACHINE |  |  | METHOD |  |  | MATERIAL |  |  | MEASUREMENT |  |  |  | ENVIRONMENT |  |  |  | OTHERS
DRB CLOSING RANK |  |  | RANK 1 |  | RANK 2 |  |  | RANK 3 |  |  | RANK 4 |  |  | RANK 5 |  |  |  | OTHERS
<2> INVESTIGATION/IDENTIFICATION OF AFFECTED AREA, SITUATION (Define the phenomenon, mode and tendency occurrence,Etc.)
1. Findings: Bent Pin at OS test
2. Mar 12/ 0500H: Pulled checkerhead at OS test due to High Open
3. Jig assembly has a retraction checking after repair of checkerhead
4. Affected units were not detected during sampling inspection.
<3> CONTAINMENT ACTION (Note: Do not disable the interlock system when doing the action) | [15 empty] | Responsible |  |  | Completion Date |  |  | Status
Name / Block
1. Pull out affected operator and decertify the process | [15 empty] | Mfg/Mtt |  |  | 2019-03-18 |  |  | Done
2. Get actual 1 unit at FVI to validate if really not detected by OS Test Inspector | [16 empty] | Mitch |  | 2019-03-18 |  |  | 6/9 inspector not detected <including affected inspector
3. Correlate all Test Operator | [16 empty] | QC I-Lanie |  | 2019-03-25 |  |  | Done
<4> DISPOSITION OF AFFECTED LOT AND RISK ASSESSMENT
Assessment Item (# of sample/Method) |  |  |  | Responsible Name / Block |  |  | Completion Date |  |  | Assessment Result (No Good/TTL QTY) | [5 empty] | Judgment (OK/NG) |  |  | Final Disposition
3592/100% inspection <P7736300> |  |  |  | Bhel-FVI |  |  | 2019-03-15 |  |  | 820/3592 | [5 empty] | NG
3589/100% inspection <P7736610> |  |  |  | Bhel-FVI |  |  | 2019-03-15 |  |  | 1731/3589 | [5 empty] | NG |  |  |  | Proceed |  | Qty : ______________________________
2951/100% inspection <P7645840> |  |  |  | Bhel-FVI |  |  | 2019-03-15 |  |  | 1488/2951 | [5 empty] | NG |  |  |  | Piece Out |  | Qty : _______ Pnl #: ________________
3283/100% inspection <P7728090> |  |  |  | Bhel-FVI |  |  | 2019-03-15 |  |  | 167/3283 | [5 empty] | NG |  |  |  | Sheet Out |  | Qty : ______________________________
[20 empty] | Lot Out |  | Qty : ______________________________
SDR
Risk Assessment Category | [10 empty] | Remarks
|  | Low |  | Medium |  |  |  | High |  |  | ________________________
<5>ACTION REQUIRED (Note: Do not disable the interlock system when doing the action)
Action Request | [9 empty] | Responsible Name / Block | [5 empty] | Completion Date |  |  | Detail Results
1. Provide actual dent sample to use in inline examination and MSB updating | [9 empty] | QC Lanie/MFG Mitch | [5 empty] | ww12.1 |  |  | Actual unit already endorsed
2. Eye test result of OS members from clinic | [9 empty] | MFG Mitch | [5 empty] | ww12.1 |  |  | Ongoing approval by clinic and HR team(all medical result is confidential)
3. Dissemination to all members for standard inspection stroke and correct magnification and sampling quantity | [9 empty] | MFG Mitch | [5 empty] | ww12.1 |  |  | Done
4. Correlate and resimulate by QA the actual defect mode the inspectress at OS test | [9 empty] | QC Lanie/MFG Mitch | [5 empty] | ww12.5 |  |  | 14/39 done, still ongoing
5. Updating of OS MSB- Dent on AU pad | [9 empty] | QC Lanie | [5 empty] | ww13 |  |  | Done
<6> ROOTCAUSE GENERATION/ANALYSIS <WHY ANALYSIS by 5M1E, DESIGN AND CAPABILITY>
1. FACTOR GAP ANALYSIS
| Problem/Issue |  | Gap Type |  | 1st why |  |  |  | 2nd why | [5 empty] | 3rd why | [5 empty] | 4th why |  |  | 5th why
| Dent on AU pad |  | Technical |  | No retraction of Pin |  |  |  | Bended Pin | [5 empty] | Possible FM attached on affected Pin during continuous Loading
Systemic
|  |  | Detection |  | Not able to detect during sampling inspection |  |  |  | Possible not following SOP on inspection sampling and BKM | [5 empty] | Under investigation
2. FINAL ROOT CAUSE and MECHANISM OF AFFECTED ISSUE
Bent pin of Checker Head
<7> CORRECTIVE ACTION | [12 empty] | Responsible |  |  |  | Completion Date |  |  | Status |  |  | Need CN & DR?
[13 empty] | Name / Block | [9 empty] | Yes | No
1. MSB enhancement | [12 empty] | QC-Lanie |  |  |  | ww13.2 |  |  | Done |  |  |  | ✓
2. Inspectress correlation on inspection, BKM assessment | [12 empty] | MFG-Mitch/QC-Lanie |  |  |  | ww12.3 |  |  | Done |  |  |  | ✓
3. Enhancement of sampling inspection every chekerhead pull out and re install <from 1 tray to 2 trays,only on chekerhead affected side>, include on work procedure | [12 empty] | MFG-Mitch |  |  |  | ww13.5 |  |  | Done |  |  |  | ✓
<8> PREVENTIVE ACTION | [12 empty] | Responsible |  |  |  | Completion Date |  |  | Status |  |  | Need CN & DR?
[13 empty] | Name / Block | [9 empty] | Yes | No
<9> PROLIFERATION | [15 empty] | Responsible |  |  | Completion |  |  | Status
[16 empty] | Name / Sign |  |  | Date
Product |  | Block | Process/line |  | Machine |  | Proliferate Item
1
2
<10>AMOUNT OF LOSS . The total sum $7,731.44
Product |  |  |  |  | Unit Qty | [7 empty] | Amount of Loss | [6 empty] | Remarks
Kabylake 4+2 LGA |  |  |  |  | 4206 | [7 empty] | 7731.44
<11> CLOSING APPROVAL (The approver person in charge should put details of the validation and closing confirmation result)
The Validation activity | [16 empty] | Closing Approver |  |  |  |  | Closing Date
ASM Gloria Reyes
QA-SCAR-MRB-02-00-01 Rev. 11