## IPI DRB Minutes
|  | IBIDEN PHILIPPINES, INC. | [17 empty] | DRB/MRB No. : |  | D-BE-19-11-002
|  | DRB/MRB REPORT MINUTES | [17 empty] | RFC No. : |  | 24-1119-0338
Theme: |  |  | Dent on Au Pad at OS Test26
Meeting Date : |  |  | 2019-12-04 | [11 empty] | Originated by : |  |  |  |  | Bryan Alberto
Meeting Time: |  |  | 1500H-1600H | [16 empty] | Name /Block
Meeting Place: |  |  | Be2 Gowning | [11 empty] | Approved by : |  |  |  |  | Lysa Salvador
Chairman: |  |  | Bryan Alberto | [15 empty] | Originator ASM/SM/DGM/GM
Block: |  |  | Be2
Attendees : |  |  | Manufacturing |  |  | Engineering/NPD |  |  | Facilities/EE |  |  |  |  | QA/QC |  |  |  |  | PPIC/CSE |  |  |  | Other
|  |  | Bryan |  |  | Jigs |  |  |  | NA |  |  |  |  | Jake
<1>PROBLEM STATEMENT : (Put another sheet if multiple lots was discovered affected)
DEFECT ISSUE: |  |  | Dent on Au Pad at OS Test26 |  | # | PRODUCT/MODEL AFFECTED |  |  | PRODUCT FAMILY |  |  | LEDGER NO. |  | PRODUCT SIZE |  | LOT NUMBER |  |  | AFFECTEDLAYER |  | AFFECTED PANEL |  | AFFECTED UNIT OR IF PERCENTAGE
DATE/TIME OCCURRED: |  |  | Nov-25-19 |  | 1 | IPI Coffeelake LGA 6+2 |  |  | CPU |  |  | 779-0074 |  | 37.5x37.5 |  | P7925810 |  |  | NA |  | NA |  | 134units/3.86%
PROCESS DETECTED: |  |  | OS |  | 2 | IPI Coffeelake LGA 6+2 |  |  | CPU |  |  | 779-0074 |  | 37.5x37.5 |  | P7925970 |  |  | NA |  | NA |  | 1728units/49.46%
PROCESS AFFECTED: |  |  | OS |  | 3 | IPI Coffeelake LGA 6+2 |  |  | CPU |  |  | 779-0074 |  | 37.5x37.5 |  | P7925780 |  |  | NA |  | NA |  | 1780units/49.97%
# OF AFFECTED LOTS : |  |  | 8 |  | 4 | IPI Coffeelake LGA 6+2 |  |  | CPU |  |  | 779-0074 |  | 37.5x37.5 |  | P7925260 |  |  | NA |  | NA |  | 1763units/46.62%
WHO DETECTED: |  |  | OS Optr. Avegail |  | 5 | IPI Coffeelake LGA 6+2 |  |  | CPU |  |  | 779-0074 |  | 37.5x37.5 |  | P7926000 |  |  | NA |  | NA |  | 1656units/48.84%
[5 empty] | 6 | IPI Coffeelake LGA 6+2 |  |  | CPU |  |  | 779-0074 |  | 37.5x37.5 |  | P7926200 |  |  | NA |  | NA |  | 1751units/49.26%
[5 empty] | 7 | IPI Coffeelake LGA 6+2 |  |  | CPU |  |  | 779-0074 |  | 37.5x37.5 |  | P7925450 |  |  | NA |  | NA |  | 1748units/49.97%
[5 empty] | 8 | IPI Coffeelake LGA 6+2 |  |  | CPU |  |  | 779-0074 |  | 37.5x37.5 |  | P7925770 |  |  | NA |  | NA |  | 882units/26.72%
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
WHAT IS THE PROBLEM DIFFERENCE FROM NORMAL TO ABNORMAL SITUATION? CHANGING POINT? DISCUSS THE FLOW. (Indicate 5W and 1H)
During processing encountered high open issue on Tester1 & Tester2 upper of OS26. Operator stopped the mc & pulled out affected checkerhead & send for toolings verification. After returning the repaired Checkerhead, lot on partial stack was processed on P7925810 Which is based on loading this is the 1st lot affected of Dent on Au Pad.
THE AGENDA ITEM IS RECURRENCE? |  |  |  | RECURRENCE |  |  | NEW |  |  |  | Recurrence Definition |  |  |  | 1. Rootcause is clear happened in same MC and parts 2. Rootcause is not clear but same issue 3. The Action was not proliferated to other process and machine but it was discussed during the meeting
THE AGENDA ITEM IS ESCAPEE? |  |  |  | YES |  |  | NO
PROBLEM CATEGORY |  |  | MAN |  | MACHINE |  |  | METHOD |  |  | MATERIAL |  |  | MEASUREMENT |  |  |  | ENVIRONMENT |  |  |  | OTHERS
DRB CLOSING RANK |  |  | RANK 1 |  | RANK 2 |  |  | RANK 3 |  |  | RANK 4 |  |  | RANK 5 |  |  |  | OTHERS
<2> INVESTIGATION/IDENTIFICATION OF AFFECTED AREA, SITUATION (Define the phenomenon, mode and tendency occurrence,Etc.)
<3> CONTAINMENT ACTION (Note: Do not disable the interlock system when doing the action) | [15 empty] | Responsible |  |  | Completion Date |  |  | Status
Name / Block
1 | Pull out affected checker head, conduct cleaning & check pin condition | [14 empty] | Bryan/Mfg |  |  | ww48.2 |  |  | Done
2 | Pull out affected optr & re-certification | [14 empty] | Bryan/Mfg |  |  | ww48.3 |  |  | Done
3 | Transfer to other process without inspection method (CCM) | [14 empty] | Bryan/Mfg |  |  | ww48.3 |  |  | Done
<4> DISPOSITION OF AFFECTED LOT AND RISK ASSESSMENT
Assessment Item (# of sample/Method) |  |  |  | Responsible Name / Block |  |  | Completion Date |  |  | Assessment Result (No Good/TTL QTY) | [5 empty] | Judgment (OK/NG) |  |  | Final Disposition
N/A
[20 empty] | Proceed |  | Qty : ______________________________
[20 empty] | Piece Out |  | Qty : 12154 Pnl #: ________________
[20 empty] | Sheet Out |  | Qty : ______________________________
[20 empty] | Lot Out |  | Qty : ______________________________
SDR
Risk Assessment Category | [10 empty] | Remarks
|  | Low |  | Medium |  |  |  | High |  |  | ________________________
<5>ACTION REQUIRED (Note: Do not disable the interlock system when doing the action)
Action Request | [9 empty] | Responsible Name / Block | [5 empty] | Completion Date |  |  | Detail Results
1. Inspection correlation for inspectress detection of dent on LGA | [9 empty] | Inspection team: Mhean | [5 empty] | WW48.3 |  |  | Done, 10/39 operators did not detect the defect
2. Segregation of marginal and NG for affected units | [9 empty] | MFG: Mitch | [5 empty] | WW48.3 |  |  | no need to segragate, peiced out all affected units.
3. Check abnormality of P7925810 from SNG ULD to OS LD | [9 empty] | MFG: Mitch | [5 empty] | WW48.3 |  |  | No abnormality found
4. 3 members unable to detect dent need to correlate the inspection effectiveness | [9 empty] | Inspection team: Mhean | [5 empty] | WW48.3 |  |  | Done, all are certified and class A
5. Re dissemination of proper checking of nozzle alignment to head and unit every product switching and every pull out of head | [9 empty] | MFG: Mitch | [5 empty] | WW48.3 |  |  | Done. Already implemented, DA will be given to those who are violating.
6. Request FAC to check IONIZER and vacuum condition | [9 empty] | MFG: Mitch FAC: Jimmy | [5 empty] | WW48.3 |  |  | Done. Already checked by FAC (headed by S'Jimmy)
Action Request | [9 empty] | Responsible Name / Block | [5 empty] | Completion Date |  |  | Detail Results
1. Conduct SEM Analysis for the FM (just like actual FM attached CH). | [9 empty] | Drew / Engg | [5 empty] | WW49.4
2. Keep and endorse to Engg FM attached on checkerhead for SEM analysis. | [9 empty] | M'Lanie / Tooling | [5 empty] | WW49.4 |  |  | should disseminate to Jig Assembly operators
3. PR microscope for OS test sampling inspection. | [9 empty] | Bryan, Mitch / Mfg | [5 empty] | WW49.4 |  |  | Refer from the quotation sent by Shin-san
4. Check the PIN HEIGHT for CH# 300-IP4D-03 (CFL 6+2 LGA). | [9 empty] | M'Lanie / Tooling | [5 empty] | WW49.4 |  |  | as per JA specs is at 25-50 um
<6> ROOTCAUSE GENERATION/ANALYSIS <WHY ANALYSIS by 5M1E, DESIGN AND CAPABILITY>
1. FACTOR GAP ANALYSIS
| Problem/Issue |  | Gap Type |  | 1st why |  |  |  | 2nd why | [5 empty] | 3rd why | [5 empty] | 4th why |  |  | 5th why
| Dent on Au pad |  | Technical
|  |  | Systemic |  | Harden fm attached on checker head |  |  |  | Under investigation
|  |  | Detection |  | Not Familiar on Defects |  |  |  | 1st time encountered the defect | [5 empty] | No actual similar defect during the training and exam.
2. FINAL ROOT CAUSE and MECHANISM OF AFFECTED ISSUE
<7> CORRECTIVE ACTION | [12 empty] | Responsible |  |  |  | Completion Date |  |  | Status |  |  | Need CN & DR?
[13 empty] | Name / Block | [9 empty] | Yes | No
1. Improve training system: Strengthen Defect Familiarization. | [12 empty] | Mhean- QA Bryan |  |  |  | WW51 |  |  | Done. Actual unit with Dent on pad is already included in inspection exam.
<8> PREVENTIVE ACTION | [12 empty] | Responsible |  |  |  | Completion Date |  |  | Status |  |  | Need CN & DR?
[13 empty] | Name / Block | [9 empty] | Yes | No
1. Include in training actual dent on Au pad defect on training and examination of OS operators. | [12 empty] | Mhean- QA Bryan |  |  |  | WW51 |  |  | Done
<9> PROLIFERATION | [15 empty] | Responsible |  |  | Completion |  |  | Status
[16 empty] | Name / Sign |  |  | Date
Product |  | Block | Process/line |  | Machine |  | Proliferate Item
1
2
<10>AMOUNT OF LOSS . The total sum 23,439.11
Product |  |  |  |  | Unit Qty | [7 empty] | Amount of Loss | [6 empty] | Remarks
Coffeelake 6+2 LGA |  |  |  |  | 12154 | [7 empty] | 23439.11
<11> CLOSING APPROVAL (The approver person in charge should put details of the validation and closing confirmation result)
The Validation activity | [16 empty] | Closing Approver |  |  |  |  | Closing Date
DGM Nobuyuki Ito
QA-SCAR-MRB-02-00-01 Rev. 11